## Sheet1
No. | Backlog Item (User Story / Task) | Task Description | Priority | Estimated Time(hours) | Assignees | Status
1 | Design UI Diagrams | Draw diagram using StarUML based on updated features in Vision Document | High | 8 | Quang Thoại, Huyền Vy | Done
2 | Write Use-case Specification | Describe each use-case: basic flow, alternative flows, pre/post-condition | High | 6 | Bảo Uyên, Quang Thoại | Done
3 | Create Sprint 2 Backlog | List and assign Sprint 2 tasks for all members | Low | 1 | Thái Bảo, Tài Phúc | Done
4 | Write Weekly Report 3 | Summarize work progress and issues in Week 03 | Low | 1 | All members | Done
5 | Write Weekly Report 4 | Summarize work progress and issues in Week 04 | Low | 1 | All members | Done
6 | Revise Project Plan Document | Revise based on TA feedback, update schedule and details | Medium | 3 | Thái Bảo, Huyền Vy | In Progress
7 | Revise Vision Document | Update requirements, user environments, highlight changes in blue | Medium | 3 | Huyền Vy, Thái Bảo | In Progress
8 | Design Software Architecture (SAD) | Choose architecture style, define main components | High | 5 | Quang Thoại, Huyền Vy | To Do
9 | Design Class Diagram | Draw class diagrams from software architecture | Medium | 4 | Huyền Vy, Thái Bảo | To Do
10 | Design Database (ERD) | Descibe table structure and relationships in the system | High | 6 | Quang Thoại, Tài Phúc | To Do